## Setup
CONSTRUCTION BUDGET TRACKER — Project Setup
Field | Value | Notes / Instructions
Project Name | My House Build | Your project name
Total Budget | 250000 | Total budget excl. VAT (numbers only)
Currency | € | Symbol only: € $ £ CHF
VAT % | 21 | Default VAT % applied to invoices
Start Date | 2026-03-01 | Format: YYYY-MM-DD
End Date | 2027-09-30 | Format: YYYY-MM-DD
Blue text = cells you should fill in
Do NOT change sheet names — the tracker reads them by name

## Categories
Trade Categories — add one row per trade / work package
Category | Budget (excl. VAT) | Notes
Foundation | 42000 | Earthworks, concrete footings, drainage
Structure | 85000 | Steel/timber frame, floors, load-bearing walls
Roof | 28000 | Roof structure, tiles/membrane, gutters
Electrical | 18000 | Rough-in wiring, distribution board, sockets
Plumbing | 22000 | Rough-in pipes, bathroom fit-out, hot water
Insulation | 15000 | Cavity wall, roof insulation, HVAC
Windows & Doors | 30000 | Frames, glazing, exterior doors
Finishing | 65000 | Plastering, tiling, painting, flooring
Landscaping | 20000 | Driveway, garden, fencing
Contingency | 25000 | Unforeseen costs — recommend 5–10% of total
TOTAL | 350000
Add new rows above the TOTAL row. Column A = category name, Column B = budget excl. VAT.

## Invoices
Invoices — log every payment / invoice here
Date | Supplier | Category | Amount (excl. VAT) | VAT % | Total (incl. VAT) | Status | Notes
2026-03-15 | Example Contractor NV | Foundation | 18500 | 21 | 22385 | paid | First batch concrete
2026-04-01 | Example Contractor NV | Foundation | 23500 | 21 | 28435 | paid | Completion payment
2026-04-20 | Example Builder BV | Structure | 40000 | 21 | 48400 | paid | Frame phase 1
2026-05-10 | Example Builder BV | Structure | 26300 | 21 | 31823 | pending | Frame phase 2
2026-04-28 | Dakwerken Peeters | Roof | 31920 | 21 | 38623.2 | paid | Full roof incl. insulation
2026-05-05 | Electro Janssen | Electrical | 8100 | 21 | 9801 | pending | Rough-in wiring
2026-05-12 | Sanitair Maes | Plumbing | 6160 | 21 | 7453.6 | pending | Rough-in pipes
Status must be: paid / pending / overdue ¦ Category must match a name from the Categories sheet

## Summary
Summary — auto-calculated reference (import into tracker to refresh)
Metric | Value
Project Name | My House Build
Total Budget | 250000
Currency | €
VAT % | 2100%
Start Date | 2026-03-01
End Date | 2027-09-30
Total Category Budget | 350000
Total Spent (incl. VAT) | 186920.8
Remaining Budget | 63079.2
% Budget Used | 0.74768
Total Invoices | 7
Paid Invoices | 4
Pending Invoices | 3
Overdue Invoices | 0
This sheet is updated automatically when you export from the tracker website.